## Side-by-side
Step | Details | Duration | Status | Comments
0. Pre-migration/Prerequisite check |  |  | Pending
0.a. Ensure that there are no locks on your virtual network, resource groups, resources, or subscription. Locks block platform operations during migration. | https://learn.microsoft.com/en-us/azure/azure-resource-manager/management/lock-resources?tabs=json#configure-locks |  | Pending
0.b. Ensure that no Azure policies are blocking actions that are required for the migration, including subnet modifications and Azure App Service resource creations. Policies that block resource modifications and creations can cause migration to get stuck or fail. |  |  | Pending
0.c. Ensure you have scaled your environment to the desired size |  |  | Pending
0.d. Ensure you have have a new available subnet for the new ASEv3, and that there is nothing blocking communication between the ASEv2 and ASEv3 subnets. The new subnet must be in the same vnet as the ASEv2 subnet. | Select a subnet in your App Service Environment v3 that meets the subnet requirements for App Service Environment v3. Note the name of the subnet you select. This subnet must be different than the subnet your existing App Service Environment is in. https://learn.microsoft.com/en-us/azure/app-service/environment/networking#subnet-requirements |  | Pending
0.e. If you need to enable zone redundancy, check if the region supports zone redundancy. | https://learn.microsoft.com/en-us/azure/app-service/environment/overview#regions
1. Select the subnet for your new App Service Environment v3 |  |  | Pending
2. Get your App Service Environment ID | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#2-get-your-app-service-environment-id |  | Pending
3. Validate migration is supported. Validate migration a couple days in advance of your scheduled migration time. As part of validation, we are checking if your ASE is on the minimum build set for migration. If not, an upgrade is automatically started to get your ASE to the latest build. Upgrades can take 8-12 hours depending on the size of the ASE and will block scaling actions and the migration from starting. You won't be able to start the migration until the upgrade finishes. | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#3-validate-migration-is-supported |  | Pending
4. Generate outbound IP addresses for your new App Service Environment v3 | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#4-generate-outbound-ip-addresses-for-your-new-app-service-environment-v3 | 15 minutes | Pending
4.a. Enable zone redundancy (optional, if you wish ensure Item 0.e. is satisfied)
5. Update dependent resources with new outbound IPs | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#5-update-dependent-resources-with-new-outbound-ips |  | Pending
5.a. NSG? |  |  | Pending
5.b. Firewall? |  |  | Pending
5.c. Route table? |  |  | Pending
6. Delegate your new App Service Environment subnet | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#6-delegate-your-app-service-environment-subnet |  | Pending
7. Confirm there are no locks on the virtual network | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#7-confirm-there-are-no-locks-on-the-virtual-network |  | Pending
8. Prepare your configurations | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#8-prepare-your-configurations |  | Pending
8.a. Configure custom domain suffix for new ASEv3 (optional for ILB only) | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-custom-domain-suffix?pivots=experience-azp |  | Pending
9. Migrate to App Service Environment v3 and check status | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#9-migrate-to-app-service-environment-v3-and-check-status | 3- 6 hours | Pending
10. Get the inbound IP addresses for your new App Service Environment v3 and update dependent resources | https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#10-get-the-inbound-ip-addresses-for-your-new-app-service-environment-v3-and-update-dependent-resources |  | Pending
11. Run validation tests on your new ASEv3 | This step is your opportunity to test and validate your new App Service Environment v3. Your App Service Environment v2 front ends are still running, but the backing compute is an App Service Environment v3. If you're able to access your apps without issues, that means you're ready to complete the migration. |  | Pending
| If any issue arise, DO NOT RUN COMMAND TO REDIRECT TRAFFIC (Step 12) and contact Azure support immediately to revert to old App Service environment. | 3-6 hours
12. Redirect customer traffic and complete migration | Proceed once all validation tests are completed. |  | Pending
Once you're ready to redirect traffic, you can complete the final step of the migration. This step updates internal DNS records to point to the load balancer IP address of your new App Service Environment v3 and the front ends that were created during the migration. Changes are effective within a couple minutes. If you run into issues, check your cache and TTL settings. This step also shuts down your old App Service Environment and deletes it. Your new App Service Environment v3 is now your production environment.
https://learn.microsoft.com/en-us/azure/app-service/environment/how-to-side-by-side-migrate#11-redirect-customer-traffic-and-complete-migration
13. Troubleshooting | https://learn.microsoft.com/en-us/azure/app-service/environment/side-by-side-migrate#troubleshooting
14. Post-migration
14.a. Optimize Isolated v2 plans | Once your upgrade is complete, you can optimize the App Service plans for additional benefits.
Review the autoselected Isolated v2 SKU sizes and scale up or scale down your App Service plans as needed.
- Scale down your App Service plans
- App Service Environment post-migration scaling guidance
Explore reserved instance pricing, savings plans, and check out the pricing estimates if needed.
- App Service pricing page
- How reservation discounts apply to Isolated v2 instances
- Azure pricing calculator